### ID Task

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 0 |  | Mode | 0 | POF Project second | 71 days | Mon 03/02/20 | Mon 11/05/20 |  |
|  |  |  |  | semester |  |  |  |
| 1 |  |  | 1 | Marching Cubes |  | Mon 03/02/20 |  |
| 2 |  |  | 1.1 | Implementing Marching Cubes | 10 days | Mon 17/02/20 | Fri 28/02/20 |
| 3 |  |  | 1.2 | Testing Marching Cubes | 10 days | Mon 02/03/20 | Fri 13/03/20 | 2 |
| 4 |  |  | 2 | Algorithms | 71 days | Mon 03/02/20 | Mon 11/05/20 |  |
| 5 |  |  | 2.1 | Researching Algorithms | 45 days | Mon 03/02/20 | Fri 03/04/20 |  |
| 6 |  |  | 2.1.1 | Time and Space Complexity's comparison of the algorithm to be | 30 days | Mon 03/02/20 | Fri 13/03/20 |  |
|  |  |  |  | selected |  |  |  |  |

WBS Task Name Duration Start Finish Predecessors

03 Feb '20 10 Feb '20 17 Feb '20 24 Feb '20 02 Mar '20 09 Mar '20 16 Mar '20 23 Mar '20 30 Mar '20 06 Apr '20 13 Apr '20 20 Apr '20 27 Apr '20 04 May '20 11 M S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T









# 7 2.1.2 Performance testing 10 days Mon 02/03/20 Fri 13/03/20 6SS+20 days of system

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | 2.1.3 | Development of algorithms | 15 days | Mon 16/03/20 | Fri 03/04/20 | 7 |  |  |
| 9 | 2.1.4 | To decide | 0 days |  |  |  |  | 03/02 |
| 10 | 2.2 | Implementing Algorithms | 16 days | Mon 06/04/20 | Mon 27/04/20 |  |  |  |
| 11 | 2.2.1 | Implementing for particle's surface | 8 days | Mon 06/04/20 | Wed 15/04/20 | 8 |  |  |
| 12 | 2.2.2 | Implementing for visualization | 8 days | Thu 16/04/20 | Mon 27/04/20 | 11 |  |  |
| 13 | 2.3 | Testing | 10 days | Tue 28/04/20 | Mon 11/05/20 |  |  |  |

14 2.3.1 Testing for particles's 5 days Tue 28/04/20 Mon 04/05/20 12

surface

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 15 | 2.3.2 | Testing for | 5 days | Tue 05/05/20 | Mon 11/05/20 | 14 |
|  |  | visualization |  |  |  |  |

## Project: POF Project second sem Date: Sat 14/12/19



Task Split

Milestone

Summary Project Summary Inactive Task

Inactive Milestone Inactive Summary Manual Task



Duration-only

Manual Summary Rollup Manual Summary



Start-only Finish-only External Tasks

External Milestone Deadline

Critical

Critical Split Progress Manual Progress

## Page 1

