## ID WBS Task Mode

Task Name Duration Start Finish Predecessors

16 Sep '19 23 Sep '19 30 Sep '19 07 Oct '19 14 Oct '19 21 Oct '19 28 Oct '19 04 Nov '19 11 Nov '19 18 Nov '19 25 Nov '19 02 Dec '19 09 Dec '19 16 Dec '19 23 Dec '19 30 Dec '19 06 Jan '20 13 Jan '20 20 Jan '20 27 Jan '20 03 Feb '20 10 Feb '20

S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S M T W T F S S

# 0 0 POF\_Project\_First\_Semester 101 days Mon 16/09/Mon 03/02/

1 1 Select project Topic 5 days Mon 16/09/1Fri 20/09/19

Baran,Cihan,ismail

2 2 Researching the necessary platform

15 days Mon 23/09/19

Fri 11/10/19 1

Baran,Cihan

3 3 Studying of Unity platform 15 days Mon 23/09/1Fri 11/10/19 1

4 4 Divide Cells Algorithm 18 days Mon 07/10/1Wed 30/10/1

ismail,Baran

5 4.1 Researching of divide cells algorithm

10 days Mon 07/10/19

Fri 18/10/19

Baran,Cihan,ismail

6 4.2 Implementing of divide cells algorithm

5 days Mon 21/10/19

Fri 25/10/19 5

Baran

7 4.3 Testing of no simulation platform

3 days Mon 28/10/19

# Wed 6

# 30/10/19

Baran

ismail,Cihan

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 8 | 5 |  |  | Preparing the RSD document | 10 days | Mon 28/10/1Fri 08/11/19 |
| 9 | 6 |  |  | Surface Particle Algorithm | 20 days | Thu 31/10/1 Wed 27/11/1 |

# 10 6.1 Researching of surface particle algorithm

# 10 days Thu 31/10/19

# Wed 7

# 13/11/19

Baran

# 11 6.2 Implementing of surface particle algorithm

# 5 days Thu 14/11/19

# Wed 10

# 20/11/19

Baran

# 12 6.3 Testing of no simulation platform

# 3 days Thu 21/11/19

# Mon 11

# 25/11/19

Baran

# 13 6.4 Find surface particle constant 2 days Tue 26/11/19Wed 27/11/112 Baran

14 7 Zhu Bridson algorithm

# 15 7.1 Researching of Zhu Bridson algorithm

# 10 days Thu 28/11/19

# Wed 13

# 11/12/19

Cihan,ismail,Baran

# 16 7.2 Implementing of Zhu Bridson 5 days Thu

# Wed 15

Baran,Cihan

# algorithm

# 12/12/19

# 18/12/19

# 17 7.3 Testing of no simulation platform

# 3 days Thu 19/12/19

# Mon 16

# 23/12/19

Baran

# 18 8 Preparing the RSD2 document 15 days Mon 18/11/19

# Fri 06/12/19

Baran,Cihan,ismail

# 19 9 Preparing the DSD document 10 days Wed 27/11/19

# Tue 10/12/19

Baran,Cihan

# 20 10 Preparing the Final report document

# 15 days Mon 02/12/19

# Fri 20/12/19

Baran,Cihan,ismail

# 21 11 Web Poster Design 5 days Mon 23/12/1Fri 27/12/19

Baran,Cihan,ismail

# 22 12 Researching of Marching Cubes 30 days Tue

# Mon 17

Baran,Cihan,ismail

algorithm

24/12/19

03/02/20

Project: POF\_Project\_First\_Seme Date: Sat 14/12/19

Task Split

Milestone

Summary

Project Summary Inactive Task

Inactive Milestone Inactive Summary Manual Task

Duration-only

Manual Summary Rollup Manual Summary



Start-only Finish-only External Tasks

External Milestone Deadline

Critical

Critical Split Progress Manual Progress

Page 1

